## Complete Load
Step # | Name | Type | Status | Folder Location | Instructions/Document | Notes
1 | Base Configuration | UI/Scripts | Not Done | 01 - Base Configuration | Base ESO Configuration | This step is only needed when loading data into an empty database provided by JDA. If a pre-configured "Gold" database is used, do not following this step.
2 | Read Process Documentation | Word Doc | Not Done | Documentation | Read the document "BC to ESO - Process Overview and Spreadsheet Instructions."
3 | Business Unit | E&L - No Review | Not Done | 02 - Business Unit (Skip) | Deprecated, unless instructed to use. | Skip this step, to be done by a Speedway Process
4 | Org Hierarchy | E&L - No Review | Not Done | 03 - Org Hierarchy (Skip) | Deprecated, unless instructed to use. | Skip this step, to be done by a Speedway Process
5 | Business Unit Group | E&L - No Review | Not Done | 04 - Business Unit Group | Execute the cmd files for step 1 & Step 2. Copy the xml files in the ESO import directory for business unit groups and import the file. | There are separate step 1 cmd files depending on if the data is to be extracted from production or a cert environment.
6 | ReSeed Before Data Import | SQL Script | Not Done | 05 - ReSeed Before Data Import | Execute the SQL script "Reseed Before Data Import.sql" in the main ESO database | This will ensure the id values for the imported configuration data starts at 10,000,001. Note: If at any point there is significant break in run this to ensure that the id values have not been removed from cache. The script is re-runnable without adversely affecting the process, so if in doubt, run it again.
7 | Item Hierarchy | E&L - Review | Not Done | 06 - Item Hierarchy | If the file is to be reviewed: 1. Execute cmd files step 1 & Step 2 and provide excel files located in the WorkingXLS folder to data cleanse team. After the review is complete, copy the excel files to the FinalXLS folder. 2. Execute cmd files Step 3 & Step 4. 3. Copy the xml file in the ESO import directory for item category and import the file. | There are separate step 1 cmd files depending on if the data is to be extracted from production or a cert environment.
8 |  | E&L - No Review |  |  | If the file does not require review: 1. Execute cmd files step 1 & Step 2 and move the excel files located in the WorkingXLS folder to the FinalXLS folder. 2. Execute cmd files Step 3 & Step 4. 3. Copy the xml file in the ESO import directory for item category and import the file. | There are separate step 1 cmd files depending on if the data is to be extracted from production or a cert environment.
9 | Manufacturer | SQL Scripts | Not Done | 07 - Manufacturer | Follow the instructions in the word document "Manufacturer Import Process."
10 | Retail Strategies | SQL Scripts or Spreadsheet | Not Done | 08 - Retail Strategies | Follow the instructions in the word document "Retail Strategies Import Process." | Strategies can be imported via a data extract from an existing system or from a spreadsheet.
11 | Retail Item - Create XML Files | E&L - Review | Not Done | 09 - Retail Item | If the files are to be reviewed: 1. Make sure the Item Extract and Item Count for Extract do not have a max id value set, this is only applicable to incremental data loads. 2. Execute cmd files step 1 & Step 2 and provide excel files located in the WorkingXLS folder to data cleanse team. After the review is complete, copy the excel files to the FinalXLS folder. 3. Execute cmd files Step 3 & Step 4. 4. DO NOT copy the xml files in the ESO import directory. | There are separate step 1 cmd files depending on if the data is to be extracted from production or a cert environment.
12 |  | E&L - No Review |  | 09 - Retail Item | If the files do not require review: 1. Make sure the Item Extract and Item Count for Extract do not have a max id value set, this is only applicable to incremental data loads. 2. Execute cmd files step 1 & Step 2 and move the excel files located in the WorkingXLS folder to the FinalXLS folder. 3. Execute cmd files Step 3 & Step 4. 4. DO NOT Copy the xml files in the ESO import directory. | There are separate step 1 cmd files depending on if the data is to be extracted from production or a cert environment.
13 | Apply Barcode Trigger Workaround | SQL Script | Not Done | 10 - Apply Barcode Trigger Workaround | Execute the script | This is a script that drops a JDA trigger and applies a trigger that does not have the defect. For a description of the defect refer to the document, "Description of Barcode Trigger Defect."
14 | Retail Item (Load One XML file) | E&L | Not Done | 09 - Retail Item | Take one file from the Retail Item FinalXLS folder and copy it to the import folder "Item" directory and import the file. | One file needs to be loaded in order for at least one execution of the depletion rules APE job to exist in the DB.
15 | Apply APE Stored Proc Workaround for Depletion Rules | Scripts | Not Done | 11 - Apply APE Stored Proc Workaround for Depletion | Execute the script | Bypasses the creation of depletion rules. This will significantly reduce the amount of time to load the item files.
16 | Retail Item (Load Remaining XML files) | E&L - Review | Not Done | 09 - Retail Item | Copy the xml files in the ESO import directory for retail items and import the files. | All files can now be loaded because the trigger and APE job workaround has been applied
17 | Retail Item (Check and Repair) | SQL Scripts | Not Done | 09 - Retail Item | Follow the instructions in the document "Retail Item Data Check and Repair Instructions"
18 | Restore Barcode Trigger Workaround | SQL Script | Not Done | 12 - Restore Barcode Trigger | Execute the script "retail_modified_item_barcode_list_i_ORIG." | Once all files are loaded successfully, restore the original barcode trigger.
19 | Restore APE Stored Proc Workaround for Depletion Rules | SQL Script | Not Done | 13 - Restore APE Stored Proc | Execute the script "sp_ape_insert_execution_object_ORIG." | Restore the APE stored procedure to its original state.
20 | Set track flag and add an each UOM for not sold items. | SQL Script | Not Done | 14 - Set Track Flag and Each UOM for Not Sold Items | Execute the script "Set Track Flag and Each UOM for Not Sold Items." | Due to an issue with the data loading process not sold items were not processed completely. This resolves the issue.
21 | Add not sold items to tracking item group. | SQL Script | Not Done | 15 - Add Not Sold Items to Transfer Group | Execute the script "Add Not Sold Items to Transfer Group" | Due to an issue with the data loading process not sold items were not processed completely. This resolves the issue.
22 | Create Depletion Rules | SQL Script | Not Done | 16 - Create Depletion Rules | Execute the script "Recreate Depletion Rules." | Creates the rules that were bypassed with the APE procedure workaround. Note: This process submits APE jobs that required up to 1 hr. to run (depending upon the amount of data). The SQL script execution and APE logs should be checked for errors.
23 | Replace Item Hierarchy Placeholder Characters | SQL Script | Not Done | 17 - Item Hierarchy Placeholder Characters | Execute the script "Replace Item Hierarchy Placeholder Characters." | This is a workaround for a JDA bug in the item hierarchy import where single quotes are not supported in the parent category name. There are a very number of categories affected.
24 | Set Device Group | SQL Script | Not Done | 18 - Set Device Group | Execute the script "Set Device Group." | Sets all retail items to use the default device group. This was added in lieu of changing the import code because there is only one device group.
25 | Extract UOM Conversions (Optional) | SQL Script & Spreadsheet | Not Done | 19 - Extract UOM Conversions | Execute the script "Extract UOM Conversions." | This provides a cross check to make sure the conversions were entered correctly. Email the results to the data cleanse team.
26 | ReSeed Before Data Import | SQL Script | Not Done | 05 - ReSeed Before Data Import | Execute the SQL script "Reseed Before Data Import.sql" in the main ESO database | Reminder to execute in case the ticket seed values have been cleared from cache.
27 | Retail Item Groups | SQL Scripts | Not Done | 20 - Retail Item Groups | Follow the instructions in the document "Retail Item Groups Import Process."
28 | Apply Discount Index Workaround | SQL Script | Not Done | 21 - Apply Discount Index Workaround | Execute the script "Remove Discount Name Index." | Accounts for a JDA bug
29 | Special | E&L - Review | Not Done | 22 - Special | If the files are to be reviewed: 1. Make sure the Special Extract does not have a max id value set, this is only applicable to incremental data loads. 2. Execute cmd files step 1 & Step 2 and provide the excel file located in the WorkingXLS folder to data cleanse team. After the review is complete, copy the excel file to the FinalXLS folder. 3. Execute cmd files Step 3 & Step 4. 4. Copy the xml files in the ESO import directory for specials and import the file. | Specials are slightly different that the other E&L processes. A single csv file/spreadsheet is used, however multiple xml files are created, one for each special. There are two step cmd files for step 1, one for production and one for certification.
30 |  | E&L - No Review | Not Done | 22 - Special | If the files do not require review: 1. Make sure the Special Extract does not have a max id value set, this is only applicable to incremental data loads. 2. Execute cmd files step 1 & Step 2 and move the excel file located in the WorkingXLS folder to the FinalXLS folder. 3. Execute cmd files Step 3 & Step 4. 4. Copy the xml file in the ESO import directory for specials and import the files. | Specials are slightly different that the other E&L processes. A single csv file/spreadsheet is used, however multiple xml files are created, one for each special. There are two step cmd files for step 1, one for production and one for certification.
31 | Restore Discount Index | SQL Script | Not Done | 23 - Restore Discount Index | Execute the script "Apply Discount Name Index." | Renames applicable discounts and puts the index back in place.
32 | Supplier | E&L - No Review | Not Done | 24 - Supplier | Execute the cmd files for step 1 & Step 2. Copy the xml file in the ESO import directory for supplier and import the file. | There are two step cmd files for step 1, one for production and one for certification.
33 | Assign Supplier to Business Unit | E&L - No Review | Not Done | 25 - Assign Supplier to Business Unit | Execute the cmd files for step 1 & Step 2. Copy the xml file in the ESO import directory for supplier assignment and import the file. | There are two step cmd files for step 1, one for production and one for certification.
34 | Assign Supplier to Business Unit Group | E&L - No Review | Not Done | 26 - Assign Supplier to Business Unit Group | Execute the cmd files for step 1 & Step 2. Copy the xml file in the ESO import directory for supplier assignment and import the file. | There are two step cmd files for step 1, one for production and one for certification.
35 | Set Catalog Import Review Flag to False | SQL Script | Not Done | 27 - Set Catalog Import Review Flag to False | Execute the script "Set Catalog Import Review to False." | If the flag is set to true, the imports will be staged for review. This is not desired during the bulk load, so all suppliers are set not to review.
36 | Supplier Item | E&L - Review | Not Done | 28 - Supplier Item | If the files are to be reviewed: 1. Make sure the Supplier Item Extract and Supplier Item Count for Extract do not have a max id value set, this is only applicable to incremental data loads. 2. Execute cmd files step 1 & Step 2 and provide excel files located in the WorkingXLS folder to data cleanse team. After the review is complete, copy the excel files to the FinalXLS folder. 3. Execute cmd files Step 3 & Step 4. 4. Copy the xml files in the catalog ESO import directory. | There are separate step 1 cmd files depending on if the data is to be extracted from production or a cert environment.
37 |  | E&L - No Review | Not Done | 28 - Supplier Item | If the files do not require review: 1. Make sure the Supplier Item Extract and Supplier Item Count for Extract do not have a max id value set, this is only applicable to incremental data loads. 2. Execute cmd files step 1 & Step 2 and move the excel files located in the WorkingXLS folder to the FinalXLS folder. 3. Execute cmd files Step 3 & Step 4. 4. Copy the xml files in the catalog ESO import directory. | There are separate step 1 cmd files depending on if the data is to be extracted from production or a cert environment.
38 | Reset Catalog Import Review Flag | SQL Script | Not Done | 29 - Reset Catalog Import Review Flag | Execute the script "Reset Catalog Import Review Flag." | Restores the flag to its prior state.
39 | Set Supplier Packaged Item Status Code | SQL Script | Not Done | 30 - Set Supplier Packaged Item Status Code | Execute the script "Set Packaged Item Status Code." See additional details in the document "BC to ESO - Process Overview and Spreadsheet Instructions." | This is a workaround for the fact that the supplier catalog import only supports one flag, however there are two flags for supplier items.
40 | Create Missing Supplier Item Links | SQL Script | Not Done | 31 - Create Missing Supplier Item Links | Execute the script "Create Missing Supplier Item Links." | For some reason that has yet to be determined, supplier item links are not 100% established when supplier items are imported.
41 | Assign Entities to Corp for Testing (Optional) | SQL Script | Not Done | 32 - Assign Entities to Corp for Testing (Not for Prod) | Execute the script "Item - Supplier Item - Specials - Assign To Corp" | For test environments, it is desirable to assign all supplier items, inventory items, and specials to the Enterprise level. Note there is also a script to removed the assignments named "Item - Supplier Item - Specials - Clear Assignments To Corp.sql."
42 | Record Id Values | Spreasheet | Not Done | N/A | Record the maximum id values for item, supplier item, suppler, and special (retail auto combo) in the spreadsheet "Incremental Extract Id Log."
43 | Price Change Event (Optional) | E&L - No Review | Not Done | 40 - Price Change Event | Execute the cmd files for step 1 & Step 2. Copy the xml files in the ESO import directory for retail price changes and import the files. | Execute this step only if requested.
44 | Business Unit Price Change (Optional) | E&L - No Review | Not Done | 41 - Business Unit Price Change | Execute the cmd files for step 1 & Step 2. Copy the xml files in the ESO import directory for bu price changes and import the files. | Execution this step only if requested. Takes an extremely long time to load (2+ days). May not be used in production.
45 | GL Accounts | XML File Drop | Not Done | 50 - GL Accounts | This has typically been done by the consulting team. | Place the file in the GL Account import directory to be loaded into ESO.
46 | Fuel Tank Types (Optional) | SQL Scripts | Not Done | 60 - Fuel Tank Types | Follow the instructions in the document "Import Fuel Tank Types and Tanks Process." | This code and process for this has been handed over to Speedway Development, so it is a required step. The Fuel Tanks import process will not work without items. The fuel items must be created in the UI first.
47 | Fuel Tanks (Optional) | SQL Scripts | Not Done | 61 - Fuel Tanks | Follow the instructions in the document "Import Fuel Tank Types and Tanks Process."
48 | Clean up staging tables | SQL Script | Not Done | 999 - Clean Up Staging Tables | Execute the script Drop BC_Extract Tables in both the BC custom integration database, the ESO database and the ESO WH database. | Do this step after all other steps have been finished. It is not advisable to do it immediately because the work tables are valuable for diagnostics if issues arise.